## Budget
Activities | Details | Budget (MUSD) |  | 0 | 2025 | 2030 | 2040
Drinking Water Supply, Sanitation and Health Sector |  | 2818 |  | 0 | 575.5 | 1527.8 | 628.1
Strategic Axis 1 | Ensure equitable and sustainable access to affordable drinking water for all | 1656 |  | 0 | 290.8 | 970 | 395.2
|  |  |  | 0% | 17.56% | 58.57% | 23.86%
Provision 1.1 | Ensure access to adequate drinking water services in urban areas, in quantity, at home or nearby, for the urban and rural population of the three OMVG basins | 1648.5 |  |  | 283.3 | 970 | 395.2
Measure 1.1.1 | Construction / rehabilitation / strengthening and monitoring of the execution of water supply systems, treatment, storage and drinking water networks and connections in urban centres | 513.6 |  |  | 65 | 330 | 118.6
Measure 1.1.2 | Construction / rehabilitation / strengthening and monitoring of the execution of drinking water infrastructure (borehole, solar pump / electrical network, chlorination station, water tower, networks and standpipe connections), for 70% of the village population | 799.2 |  |  | 65 | 540 | 194.2
Measure 1.1.3 | Construction/rehabilitation and monitoring of BHPP implementation works for 30% of the village population. Existing boreholes are rehabilitated and strengthen drinking water points or can provide an alternative water source for livestock and agriculture | 282.4 |  |  | 100 | 100 | 82.4
Measure 1.1.4 | Conduct studies, projects and tender documents for the planning, design and detailing of solutions for the implementation of drinking water supply infrastructure in urban centres | 17.1 |  |  | 17.1 | - | -
Measure 1.1.5 | Conduct studies, projects and tender documents for the planning, design and detailing of solutions for the implementation of drinking water supply infrastructure in the villages | 36.2 |  |  | 36.2 | - | -
Provision 1.2 | Ensure the implementation of a geographic information system for drinking water supply infrastructures in the OMVG area | 2.5 |  |  | 2.5
Measure 1.2.1 | Development of a database of drinking water supply infrastructures in each of the OMVG catchment areas in liaison with the water resources agencies and the supervisory ministries of the four Member States | 2.5 |  |  | 2.5 | - | -
Provision 1.3 | Ensure governance of the sector in the context of existing and emerging challenges | 0 |  |  | 0 | 0 | 0
Measure 1.3.1 | Capacity building of the institutions responsible for the drinking water sub-sector in each of the member states and in the OMVG
Measure 1.3.2 | Training of managers of institutions responsible for the drinking water sub-sector in each of the member states and in the OMVG
Provision 1.4 | Ensure access to a sustainable, quality drinking water service | 5 |  |  | 5 | 0 | 0
Measure 1.4.1 | Training of the private sector in each country for the management, operation and maintenance of drinking water networks and BHPP | 2 |  |  | 2 | - | -
Measure 1.4.2 | Establishment/strengthening of systems for monitoring, control and technical and financial evaluation of management performance, operation and maintenance of drinking water networks and BHPP in rural areas | 3 |  |  | 3 | - | -
TOTAL Strategic Axis 1 | Ensure equitable and sustainable access to affordable drinking water for all | 1656 |  | 0 | 290.8 | 970 | 395.2
Activities | Details | Budget (MUSD) |  | Year 1 | 2025 | 2030 | 2040
Strategic Axis 2 | Ensure equitable and sustainable access to adequate sanitation and hygiene services for all and end open defecation | 823 |  | 0 | 139.1 | 451 | 232.9
|  |  |  | 0% | 16.9% | 54.8% | 28.3%
Provision 2.1 | Ensure access to adequate sanitation and hygiene services for the urban and rural population in the OMVG area | 813 |  |  | 130.1 | 450 | 232.9
Measure 2.1.1 | Construction/rehabilitation and monitoring of sanitation and hygiene infrastructure implementation works, off-site in and around the city centre, and on-site in the peri-urban areas of the cities for the population of the urban centres | 505.8 |  |  | 60 | 350 | 95.8
Measure 2.1.2 | Construction/rehabilitation and monitoring of the implementation of on-site sanitation and hygiene infrastructures for the population in rural areas | 277.1 |  |  | 40 | 100 | 137.1
Measure 2.1.3 | Conduct studies, projects and tender documents for the planning, design and detailing of solutions for the implementation of sanitation and hygiene infrastructure in urban centres | 16.9 |  |  | 16.9 | - | -
Measure 2.1.4 | Conduct studies, projects and tender documents for the planning, design and detailing of solutions for the implementation of sanitation and hygiene infrastructure in rural areas | 13.2 |  |  | 13.2 | - | -
Provision 2.2 | End OD and educate communities on good sanitation and hygiene practices | 5 |  |  | 5
Measure 2.2.1 | Mobilise and raise awareness of the population to end OD | 5 |  |  | 5 | - | -
Provision 2.3 | Ensure governance of the sector in the context of existing and emerging challenges
Measure 2.3.1 | Capacity building of institutions responsible for the sanitation and hygiene sub-sector in each of the Member States and in the OMVG
Measure 2.3.2 | Training of managers of institutions responsible for the sanitation and hygiene sub-sector in each of the Member States and in the OMVG
Provision 2.4 | Ensure access to sustainable, quality sanitation and hygiene services in the OMVG area | 5 |  |  | 4 | 1
Measure 2.4.1 | Training of the private sector in each country for the management, maintenance and operation of sanitation infrastructure in urban centres | 2 |  |  | 1 | 1
Measure 2.4.2 | Establishment/strengthening of a system for monitoring, control and technical and financial evaluation of the management, operation and maintenance performance of the sanitation service in urban centres | 3 |  |  | 3
TOTAL Strategic Axis 2 | Ensure equitable and sustainable access to adequate sanitation and hygiene services for all and end open defecation | 823 |  |  | 139.1 | 451 | 232.9
Activities | Details | Budget (MUSD) |  | Year 1 | 2025 | 2030 | 2040
Strategic Axis 3 | Ensure equity of access for all to quality health care and services and strengthen the prevention and management of communicable and non-communicable diseases | 339 |  |  | 145.6 | 106.8 | 86.6
|  |  |  | 0% | 42.95% | 31.5% | 25.55%
Provision 3.1 | Ensure the availability of functional health structures, with well-trained staff and sufficient quantity and quality of medicines for the effective care of all sections of the population | 146 |  |  | 64 | 41 | 41
Measure 3.1.1 | Construction and equipping of 30 new posts, 10 health centres and 3 referral hospitals | 30 |  |  | 30
Measure 3.1.2 | Annual recruitment of adequate health personnel (doctors, midwives, nurses, laboratory assistants, pharmacists) | 65 |  |  | 15 | 25 | 25
Measure 3.1.3 | Establish a system for the supply of quality medicines and avoidance of shortages of essential medicines in all health facilities | 10 |  |  | 5 | 3 | 2
Measure 3.1.4 | Strengthen community-based health initiatives | 41 | 14 |  | 14 | 13 | 14
Provision 3.2 | Ensure adequate financing of the health sector with the mobilisation of endogenous and external resources | 5 |  |  | 1.6 | 1.8 | 1.6
Measure 3.2.1 | Increase health expenditure to 15% of the national budget in line with commitments made by states | 1 |  |  | 0.3 | 0.4 | 0.3
Measure 3.2.2 | Stimulation of national initiatives for the mobilisation of endogenous resources (corporate social responsibility) | 1 |  |  | 0.3 | 0.4 | 0.3
Measure 3.2.3 | Implement advocacy for greater mobilisation of international financial resources | 3 |  |  | 1 | 1 | 1
Provision 3.3 | Ensure the implementation of an efficient information system with a dynamic collection of reliable health information | 16 |  |  | 7 | 7 | 2
Measure 3.3.1 | Strengthen the quality of health data with a DHIS2-based monitoring system | 10 |  |  | 5 | 5 | -
Measure 3.3.2 | Development of the skills of health workers through training in the collection, storage and maintenance of reliable and relevant health databases | 6 |  |  | 2 | 2 | 2
Provision 3.4 | Ensure access to health information, disease prevention and effective care | 124 |  |  | 45 | 43 | 36
Measure 3.4.1 | Update and disseminate guidelines for the management of diseases under surveillance | 4 |  |  | 2 | 2 | -
Measure 3.4.2 | Improve access to treatment for good patient care | 10 |  |  | 4 | 3 | 3
Measure 3.4.3 | Improve access to means of prevention against communicable diseases (pandemics) | 100 |  |  | 35 | 35 | 30
Measure 3.4.4 | Promotion of maternal and child health | 10 |  |  | 4 | 3 | 3
Provision 3.5 | Ensure an effective epidemiological surveillance system for early detection of epidemiological threats and a rapid and adequate response | 18 |  |  | 8 | 6 | 4
Measure 3.5.1 | Update and implementation of disease surveillance guidelines | 8 |  |  | 3 | 3 | 2
Measure 3.5.2 | Strengthen sentinel sites for epidemiological surveillance in the OMVG area | 10 |  |  | 5 | 3 | 2
Provision 3.6 | Ensure the establishment of equipped health structures responsible for emergency health operations at the decentralised level | 30 |  |  | 20 | 8 | 2
Measure 3.6.1 | Establishment of health emergency operations centres in peripheral regions for better preparedness against disasters and pandemics | 20 |  |  | 15 | 5 | -
Measure 3.6.2 | Establish cross-border surveillance of epidemics | 10 |  |  | 5 | 3 | 2
TOTAL Strategic Axis 3 | Ensure equity of access for all to quality health care and services and strengthen the prevention and management of communicable and non-communicable diseases | 339 |  |  | 145.6 | 106.8 | 86.6
TOTAL BUDGET Programme |  | 2818 |  |  | 575.5 | 1527.8 | 714.7

## Timeline
Program of measures
Strategic Axes, Provisions, Measures |  |  | Horizons
|  |  | 2025 |  |  |  | 2030 |  |  |  |  | 2040
|  |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Strategic Axis 1 - Ensure equitable, sustainable and affordable access to safe drinking water for all
Provision 1.1 - Ensure access to adequate drinking water services in urban areas, in quantity, at home or nearby, for the urban and rural population of the three OMVG basins
| Measure 1.1.1 | Construction / rehabilitation / strengthening and monitoring of the execution of water supply systems, treatment, storage and drinking water networks and connections in urban centres
| Measure 1.1.2 | Construction / rehabilitation / strengthening and monitoring of the execution of drinking water infrastructure (borehole, solar pump/electrical network, chlorination station, water tower, networks and standpipe connections), for 70% of the village population
| Measure 1.1.3 | Construction/rehabilitation and monitoring of BHPP implementation works for 30% of the village population. Existing boreholes are rehabilitated and strengthen drinking water points or can provide an alternative water source for livestock and agriculture
| Measure 1.1.4 | Conduct studies, projects and tender documents for the planning, design and detailing of solutions for the implementation of drinking water supply infrastructure in urban centres | bar: 2025 2023 to 2025 2025
| Measure 1.1.5 | Conduct studies, projects and tender documents for the planning, design and detailing of solutions for the implementation of drinking water supply infrastructure in the villages | bar: 2025 2023 to 2025 2025
Provision 1.2 - |  | Ensure the implementation of a geographic information system for drinking water supply infrastructures in the OMVG area
| Measure 1.2.1 | Development of a database of drinking water supply infrastructures in each of the OMVG catchment areas in liaison with the water resources agencies and the supervisory ministries of the four Member States | bar: 2025 2023 to 2025 2024
Provision 1.3 - |  | Ensuring governance of the sector in the context of existing and emerging challenges
| Measure 1.3.1 | Capacity building of the institutions responsible for the drinking water sub-sector in each of the member states and in the OMVG | bar: 2025 2023 to 2030 2030
| Measure 1.3.2 | Training of managers of institutions responsible for the drinking water sub-sector in each of the member states and in the OMVG | bar: 2025 2023 to 2030 2030
Provision 1.4 - Ensure access to a sustainable quality drinking water service
| Measure 1.4.1 | Training of the private sector in each country for the management, operation and maintenance of drinking water networks and BHPP | bar: 2025 2024 to 2025 2025
| Measure 1.4.2 | Establishment/strengthening of systems for monitoring, control and technical and financial evaluation of management performance, operation and maintenance of drinking water networks and BHPP in rural areas | bar: 2025 2023 to 2025 2025
Strategic Axes, Provisions, Measures |  |  | 2025 2022: Horizons
|  |  | 2025 |  |  |  | 2030 |  |  |  |  | 2040
|  |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Strategic Axis 2 - Ensure equitable and sustainable access to adequate sanitation and hygiene services for all and end open defecation
Provision 2.1 - Ensure access to adequate sanitation and hygiene services for the urban and rural population in the OMVG area
| Measure 2.1.1 | Construction/rehabilitation and monitoring of sanitation and hygiene infrastructure implementation works, off-site in and around the city centre, and on-site in the peri-urban areas of the cities for the population of the urban centres
| Measure 2.1.2 | Construction/rehabilitation and monitoring of the implementation of on-site sanitation and hygiene infrastructures for the population in rural areas
| Measure 2.1.3 | Conduct studies, projects and tender documents for the planning, design and detailing of solutions for the implementation of sanitation and hygiene infrastructure in urban centres | bar: 2025 2023 to 2025 2025
| Measure 2.1.4 | Conduct studies, projects and tender documents for the planning, design and detailing of solutions for the implementation of sanitation and hygiene infrastructure in rural areas | bar: 2025 2023 to 2025 2025
Provision 2.2 - |  | End OD and educating communities on good sanitation and hygiene practices
| Measure 2.2.1 | Mobilise and raise awareness of the population to end OD | bar: 2025 2023 to 2030 2030
Provision 2.3 - |  | Ensure governance of the sector in the context of existing and emerging challenges
| Measure 2.3.1 | Capacity building of institutions responsible for the sanitation and hygiene sub-sector in each of the Member States and in the OMVG | bar: 2025 2023 to 2030 2030
| Measure 2.3.2 | Training of managers of institutions responsible for the sanitation and hygiene sub-sector in each of the Member States and in the OMVG | bar: 2025 2023 to 2030 2030
Provision 2.4 - Ensure access to sustainable quality sanitation and hygiene services in the OMVG area
| Measure 2.4.1 | Training of the private sector in each country for the management, maintenance and operation of sanitation infrastructure in urban centres | bar: 2025 2025; 2030 2028
| Measure 2.4.2 | Establishment/strengthening of a system for monitoring, control and technical and financial evaluation of the management, operation and maintenance performance of the sanitation service in urban centres | bar: 2025 2023 to 2025 2025
Strategic Axes, Provisions, Measures |  |  | 2025 2022: Horizons
|  |  | 2025 |  |  |  | 2030 |  |  |  |  | 2040
|  |  | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
Strategic Axis 3 - Ensure equitable access to quality health care and services for all and strengthen the prevention and management of communicable and non-communicable diseases
Provision 3.1 - Ensure the availability of functional health structures with well-trained staff and sufficient quantity and quality of medicines for the effective treatment of all sections of the population
| Measure 3.1.1 | Construction and equipping of 30 new posts, 10 health centres and 3 referral hospitals | bar: 2025 2024 to 2025 2025
| Measure 3.1.2 | Annual recruitment of adequate health personnel (doctors, midwives, nurses, laboratory assistants, pharmacists) | bar: 2025 2024 to 2040 2040
| Measure 3.1.3 | Establish a system for the supply of quality medicines and avoidance of shortages of essential medicines in all health facilities | bar: 2025 2024 to 2025 2025; 2030 2029 to 2040 2031; 2040 2034 to 2040 2036
| Measure 3.1.4 | Strengthen community-based health initiatives | bar: 2025 2024 to 2040 2040
Provision 3.2 - Ensure adequate financing of the health sector by mobilising endogenous and external resources
| Measure 3.2.1 | Increase health expenditure to 15% of the national budget in line with commitments made by states | bar: 2025 2024 to 2040 2040
| Measure 3.2.2 | Stimulate national initiatives for the mobilisation of endogenous resources (corporate social responsibility) | bar: 2025 2025; 2030 2029; 2040 2031; 2040 2034 to 2040 2036; 2040 2038 to 2040 2039
| Measure 3.2.3 | Implement advocacy for greater mobilisation of international financial resources | bar: 2025 2025; 2030 2028; 2040 2031; 2040 2034; 2040 2037; 2040 2040
Provision 3.3 - Ensure the establishment of an efficient information system with a dynamic collection of reliable health information
| Measure 3.3.1 | Strengthen the quality of health data with a monitoring system based on DHIS2 | bar: 2025 2024 to 2040 2035
| Measure 3.3.2 | Develop the skills of health workers through training in the collection, storage and maintenance of reliable and relevant health databases | bar: 2025 2024 to 2040 2040
Provision 3.4 - Ensure access to health information, disease prevention and effective care
| Measure 3.4.1 | Update and disseminating guidelines for the management of diseases under surveillance | bar: 2025 2024; 2030 2027; 2030 2030; 2040 2033
| Measure 3.4.2 | Improve access to treatment for good patient care | bar: 2025 2025
| Measure 3.4.3 | Improve access to means of prevention against communicable diseases (pandemics) | bar: 2025 2024 to 2040 2040
| Measure 3.4.4 | Promotion of maternal and child health | bar: 2025 2024 to 2040 2040
Provision 3.5 - Ensure an effective epidemiological surveillance system for early detection of epidemiological threats and a rapid and adequate response
| Measure 3.5.1 | Update and implementation of disease surveillance guidelines | bar: 2025 2024 to 2040 2040
| Measure 3.5.2 | Strengthen sentinel sites for epidemiological surveillance in the OMVG area | bar: 2025 2024 to 2040 2040
Provision 3.6 - Ensure the establishment of equipped health structures responsible for emergency health operations at the decentralised level
| Measure 3.6.1 | Establishment of emergency health operations centres in peripheral regions for better preparedness against disasters and pandemics | bar: 2025 2024 to 2040 2040
| Measure 3.6.2 | Establish cross-border surveillance of epidemics | bar: 2025 2024 to 2040 2040