## GOODS
DATE: 29-04-2021
PROJECT TITLE: CSRWASHDEP
REGISTER OF CONTRACTS
REPORTING PERIOD: Nov 2018 to 2023
PAGE NO.____1______OF______1_____
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  |  | 9 |  |  | 10 | 11
Contract Serial No. | % of Financing | Description of Goods and related Services /Training Programes | Proc Method | Date of Contract | Name and Address of Contractor | Country of Origin | Delivery Period | Performance guarantee Expiry Date | Contract Start Date | End Date | Contract Amount(in the currency of contract) | Financial Progress (% progress) | Physical Progress (% progress) | Category (Grant/Loan) | Remarks/ Issues/challenges
CSRWASHDEP/PRO/C2/G001/F2/2019 | 100 | Procurement of 2 NISSAN hard bodied motor vehicles (Pick-up) | NCB | 2019-08-10 | Shyben A. Madi and Sons, Kanifing Industrial Estate | Gambia | 3 weeks | NA | 2019-08-10 | 2019-08-31 | D2,310,000.00 | 100 | 100 | Grant | Vehichles delivered
CSRWASHDEP/PRO/C2/G001/F3/2019 | 100 | Procurement of 1 Toyata Landcruiser Prado TXL and 1 Toyota Rush Station Wagon | NCB | 2019-08-10 | CFAO Motors Gambia, Kanifing Industrial Estate | Gambia | 8 weeks | NA | 2019-08-10 | 2019-10-10 | D3,625,000.00 | 100 | 100 | Grant | Vehichles delivered
CSRWASHDEP/PRO/C2/G002(P1)/2019 | 100 | Supply of IT Equipments | Shopping | 2019-10-09 | KMF Technologies, Kerr Serigne | Gambia | 2 weeks | NA | 2019-10-09 | 24/09/2019 | D1,383,000.00 | 100 | 100 | Grant | Delivered
CSRWASHDEP/PRO/C2/G002(P2)/2019 | 100 | Supply of IT Equipments | Shopping | 2019-10-09 | QueenTech Computers, Kairaba Avenue | Gambia | 2 weeks | NA | 2019-10-09 | 24/09/2019 | D580,000.00 | 100 | 100 | Grant | Delivered
CSRWASHDEP/PRO/C2/G002(P3)/2019 | 100 | Supply of IT Equipments | Shopping | 2019-12-09 | NIFTY Solutions, Brusubi | Gambia | 2 weeks | NA | 2019-12-09 | 26/09/2019 | D81,339.00 | 100 | 100 | Grant | Delivered
GM-CSRWASHDEP/C1/G001/2020 | 100 | Supply of Building Materials | NCB | 2021-05-10 | Santa Yallah Business Centre, Bakoteh | The Gambia |  | NA | 2021-05-24 |  | D2,823,050.00 | 100 | 100 | Grant | Delivered
NOTE: FULLY EXECUTED AND CLOSED CONTRACTS CAN BE MARKED GREEN
PREPARED BY: M &E unit |  |  |  | CERTIFIED BY: ……………………………………………….. | [6 empty] | ENDORSED BY:…………………………………………

## WORKS
DATE: 29-04-2021
PROJECT TITLE: CSRWASHDEP
PROJECT ID:
REGISTER OF CONTRACTS
REPORTING PERIOD: 2018 to 2023
(MONTH / YEAR ): NOV 2019
PAGE NO.____1______OF______1_____
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | 8a |  |  |  | 9 | 9a | 9b | 10 | 11
Contract Serial No. | % of Financing | Description of Works | Proc Method | Date of Contract signature | Name and Address of Contractor | Country of Origin | Delivery Period | Performance guarantee Expiry Date | Contract Start Date | End Date | Addenda date | end date | Addenda Amount(in the currency of contract) | Contract Amount(in the currency of contract) | Financial Progress(% progress) | Physical Progress (% progress) | Category (Grant/Loan) | Remarks/ Issues/Challenges
GM-CSRWASHDEP/C2/001/2019 | 100% | Rehabilitation and Expansion of office building -DWR | NCB | 26 Sept. 2019 | Santa Yalla Business Center, Bakoteh | The Gambia | 9 months | July 15th, 2020 | 15 Oct. 2019 | 31 Jul. 2020 | 18 Jun. 2020 | 31 Dec. 2020 | 2210280 | GMD14,836,490 | 99.77% | 100% | Grant | completed
CSRWASHDEP/PRO/C2/W001/F1/2020 | 66. 5% | Lot 1A: Drilling of 50 large boreholes in all regions of The Gambia | NCB | 5 Nov. 2020 | Heloica Energy, Madiana Salanding | The Gambia | 9 months | December 9th 2021 | 19 Nov. 2020 | 31 Aug. 2021 | 18/02/2022 |  |  | USD391,570.00 | 66.5% |  | Grant | Ongoing
CSRWASHDEP/PRO/C2/S001/F1/2020 | 71. 4% | Lot 1B: Drilling of 53 large boreholes in all regions of The Gambia | NCB | 5 Nov. 2020 | Heloica Energy, Madiana Salanding | The Gambia | 9 months | December 9th 2021 | 19 Nov. 2020 | 31 Aug. 2021 | 18/02/2022 |  |  | USD306,116.00 | 71.4% |  | Grant | Ongoing
GM-CSRWASHDEP/C1/G001/2021 | 35. 7% | Lot 1 Construction of 20 Inst. Sanitation facilities | NCB | 19 May. 2021 | Sumangura , Latri Sabiji | The Gambia | 9 Months | March 14th, 2022 | 02 Jun. 2021 | 19 Feb. 2022 | 2022-09-02 | 30/08/2022 |  | GMD 14,166,100 | 35.7% |  | Grant | Ongoing
GM-CSRWASHDEP/C1/G001/2021 | 38. 3% | Lot 2 Construction of 20 Inst. Sanitation facilities | NCB | 19 May. 2021 | Sumangura , Latri Sabiji | The Gambia | 9 Months | March 14th, 2022 | 02 Jun. 2021 | 19 Feb. 2022 | 2022-09-02 | 30/08/2022 |  | GMD13,774,100 | 38.3% |  | Grant | Ongoing
NOTE: FULLY EXECUTED AND CLOSED CONTRACTS CAN BE MARKED GREEN
| PREPARED BY:M&E unit |  |  |  | CERTIFIED BY: ……………………………………………….. |  |  |  |  | ENDORSED BY:…………………………………………

## SERVICES
DATE: 30-10-2021
PROJECT TITLE: CSRWASHDEP
PROJECT ID:
REGISTER OF CONTRACTS
REPORTING PERIOD: | 2018- 2023
PAGE NO.____1______OF______1_____
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  |  |  | 9 | 9a | 9b | 10 | 11
Contract Serial No. | % of Financing | Description of Services or Training Programes | Selection Method | Date of Contract | Name and Address of Servive Provider | Country of Origin | Delivery Period | Contract Start Date | Contract End Date | Extension | Addendum | Contract Amount(in the currency of contract) | Financial Progress(% progress) | Physical Progress (% progress) | Category (Grant/Loan) | Remarks/ Issues/challenges
CR008 | 100% | FinExPP, Accounting system and User Training and Support | LCS | 2019-05-23 | DT Associates The Gambia | The Gambia | 1 month | 2019-05-23 |  |  |  | USD 13,000 | 100% | 100% | Grant | Completed. Yearly renewal
| 100% | Effective communication | Direct sourcing | 2019-10-17 | Classik Consulting | The Gambia | 5 Days | 2019-12-15 | 2019-12-19 |  |  | GMD 90,000 | 100% | 100% | Grant | Completed
CSR/2019-C002 | 100% | Consulting Services for Training Needs Assesment | Direct sourcing | 2019-11-01 | Management Development Institute The Gambia | The Gambia | 1 month | 2019-11-03 | 11/31/2019 |  |  | GMD 218,250 | 100% | 100% | Grant | Completed
GAM-CSRWASHDEP/C2/S002(2019) | 100% | Consultancy on training of WASH sector professionals | Direct sourcing | 2019-11-06 | University of The Gambia Department of Public and Environmental Health | The Gambia | 2 weeks | 2019-11-04 | 2019-11-15 |  |  | GMD 496,800 | 100% | 100% | Grant | Completed
GM-CSRWASHDEP/C2/S001-2019 | 99.9% | KAP Survey | QCBS | 2020-12-09 | CIAM, CaDO & ADWAC (JV) | The Gambia | 6 Months | 2020-12-16 | 2021-06-16 |  |  | GMD 9,593,000 | 99. 9% |  | Grant | Ongoing
GM-CSRWASHDEP/C2/S001-2019 | 0 | Consulting services for Hygiene Promotion and Education | QCBS | 2020-12-09 | CIAM, CaDO & ADWAC (JV) | The Gambia | 24 Months | 2021-06-16 | 2023-05-31 |  |  | GMD 21,579,000 | 0% |  | Grant | Not yet started
CSRWASHDEP/C1S/001-2019 | 40% | Water supply infrastructure network design | QCBS | 2020-12-15 | CIRA SAS & SIAT SENEGAL SAS (JV) | Gambia, Mali & Senegal | 4 months | 2020-12-29 | 2021-04-29 | 2021-07-31 |  | EUR 133,366 | 40% |  | Grant | Ongoing
CSRWASHDEP/C1S/001-2019 |  | Water Supply infrastrusture Works Supervision | QCBS |  | CIRA SAS & SIAT SENEGAL SAS (JV) | Gambia, Mali & Senegal | 24 Months | Starts after network design |  |  |  | EUR 314,274 | 0% |  | Grant | Not yet started
CSRWASHDEP/C1S/001-2019 | 20% | Waste Management Study & Landfill Design For The Gambia | QCBS | 2021-05-24 | PROCESL, GIBB Engineering,& MAHFOUS Engineering Consultancy | Portugal, Italy, Gambia | 9 Months | 2021-06-07 | 2022-03-07 |  |  | EUR 315,203.48 | 20% |  | Grant | Ongoing
CSRWASHDEP/C2/S-003-2020 | 61.8% | WASH Mapping ans M&E web-based system | QCBS | 2021-06-29 | HYDRONOVA & WATER CHARITY JOINT VENTURE | Italy,The Gambia | 8 months | 20th July 2021 | 20th March 2022 | 30/04/2022 |  | EUR415,120.59 | 61.8% |  | Grant | Ongoing
CSRWASHDEP/C3/S001-2020 | 20% | Design of Municipal Waste Collection Centers | QCBS | 2021-09-29 | Ideck, SREI and Elixir global group | India & Gambia | 4 months | 2021-10-18 | 2022-02-18 | 30/06/2022 |  | USD 230,015.00 | 20% |  | Grant | Ongoing
|  | Annual Wash Sector Performance Review 2020 - 2021 | QCBS | 2021-08-12 | Frame Consultants Ltd, DevEmerg Consultancy Ltd and Institute of Social Research and Development (ISRAD) JV | Kenya & The Gambia | 3 months | 22/12/2021 | 21/03/2022 |  |  | USD 91, 500. 00 |  |  | Grant | Ongoing
SUBTOTAL
NOTE: FULLY EXECUTED AND CLOSED CONTRACTS CAN BE MARKED GREEN
| PREPARED BY: M&E unit |  |  |  | CERTIFIED BY: ……………………………………………….. | [9 empty] | ENDORSED BY:…………………………………………